## Description
Text Transformer
For people working with text data, our Text Transformer application will allow you to transform text data (e.g. change case, eliminate duplicates, etc.). The application will be available via GUI as well as remote API, thanks to which it will be possible to integrate it with existing tools.

## Product Backlog
Product Backlog item | Importance | Labour intensity | Business Value (BV) | Acceptance Criteria
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps | 15 | 10 Hours | 1 | o Input in the form of text and transformation sequence (names) o Input and output in JSON format o REST API allows to run any currently implemented transformation or transformation sequence
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) | 12 | 9 Hours | 0.5 | o Change case of letters - set of three transformations (upper, lower, capitalize) • upper - all letters to uppercase: upper -> UPPER • lower – all letters to lowercase: Lower -> lower • capitalize – the first letter in each word to uppercase: capitalize text -> Capitalize Text • Support for letters from the English alphabet (UTF-8)
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) | 10 |  | 0.5 | • Preserving the positions of upper and lower case letters: MirEk -> KerIm • Reverse sequence of characters • Support for all UTF-8 characters
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated | 10 | 7 Hours | 1 | • conversion of integers to 1000 • conversion of floating point numbers to hundredths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate | 10 |  | 0.5 | • Acronym expansion: for example -> e.g. • Acronym expansion: among others -> i.a. • Acronym expansion: and so on -> aso • Works regardless of case
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) | 10 | 7 | 0.5 | • prof. -> professor • dr -> doctor • e.g. -> for example • aso -> and so on • Preserves case: E.g. -> For example
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) | 2 |  | 0.5 | • & -> \& • $ -> \$
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) | 1 | 7 | 1 | • Convert two repeated words to one: to to -> to • Convert any number of words repeated: to to to -> to • Replace all repetitions within a text: to to after after -> to after • Works well with all UTF-8 characters
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint #1 Backlog
Sprint Goal: | Learning to work in a team, solving a complex project with the SCRUM method
Product Backlog Item | Tasks | Labour intensity
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps |  | 20 Hours
| Learning JSON | 4
| Learning Rest | 5
| Writing Code | 6
| Testing | 5
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) |  | 9
| Searching and Planing | 2
| Codeing | 5
| Testing | 2
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated |  | 7
| Searching,Learning and Planing | 3
| Codeing | 3
| Testing | 1
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) |  | 7
| Searching,Learning and Planing | 2
| Codeing | 3
| Testing | 2
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) |  | 7
| Searching,Learning and Planing | 2
| Codeing | 3
| Testing | 2

## Product Backlog#2
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps | 15 | 10 Hours | 1 | o Input in the form of text and transformation sequence (names) o Input and output in JSON format o REST API allows to run any currently implemented transformation or transformation sequence
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) | 12 | 9 Hours | 0.5 | o Change case of letters - set of three transformations (upper, lower, capitalize) • upper - all letters to uppercase: upper -> UPPER • lower – all letters to lowercase: Lower -> lower • capitalize – the first letter in each word to uppercase: capitalize text -> Capitalize Text • Support for letters from the English alphabet (UTF-8)
As a user, I can reverse the sequence of characters, retaining the case of letters in specific positions (inverse) | 10 |  | 0.5 | • Preserving the positions of upper and lower case letters: MirEk -> KerIm • Reverse sequence of characters • Support for all UTF-8 characters
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated | 10 | 7 Hours | 1 | • conversion of integers to 1000 • conversion of floating point numbers to hundredths
As a user, I can replace selected (predefined) words with acronyms (Bread is, for example rolls -> Bread is, e.g. rolls) - the range of supported shortcuts to negotiate | 10 |  | 0.5 | • Acronym expansion: for example -> e.g. • Acronym expansion: among others -> i.a. • Acronym expansion: and so on -> aso • Works regardless of case
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) | 10 | 7 | 0.5 | • prof. -> professor • dr -> doctor • e.g. -> for example • aso -> and so on • Preserves case: E.g. -> For example
As a user I can convert text to Latex supported format (special characters) -> (John Smith & Sons -> John Smith \& Sons) | 2 |  | 0.5 | • & -> \& • $ -> \$
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) | 1 | 7 | 1 | • Convert two repeated words to one: to to -> to • Convert any number of words repeated: to to to -> to • Replace all repetitions within a text: to to after after -> to after • Works well with all UTF-8 characters
As a user, I can utilise the application via the user interface |  |  |  | To be negotiated later

## Sprint#2 Backlog
Sprint Goal: | Learning to work in a team, solving a complex project with the SCRUM method
As an application developer, I can invoke a transformation remotely via REST to be able to integrate the tool with my other apps |  | 20 Hours
| Learning JSON | 4
| Learning Rest | 5
| Writing Code | 6
| Testing | 5
As a user, I can modify the case of letters - a set of three transformations (upper, lower, capitalize) |  | 9
| Searching and Planing | 2
| Codeing | 5
| Testing | 2
As a user, I can convert numbers into text in English (donate 100 dollars -> donate one hundred dollars) - support for the range of numbers to be negotiated |  | 7
| Searching,Learning and Planing | 3
| Codeing | 3
| Testing | 1
As a user, I can expand selected acronyms to full strings (Professor was late for classes -> Prof. was late for classes) |  | 7
| Searching,Learning and Planing | 2
| Codeing | 3
| Testing | 2
As a user, I can eliminate repetitive words in the immediate vicinity (Send me me a message -> Send me a message) |  | 7
| Searching,Learning and Planing | 2
| Codeing | 3
| Testing | 2